## Frontend Security Table
Voicera Frontend — Security & Compliance Table
Based on HL-SEC-DEVBRIEF-2026-001 ¦ Frontend only ¦ 13 Aug 2026 ¦ Confidential — Internal
Brief stack is Clerk / Supabase / FastAPI / Azure. Voicera frontend uses React + Firebase Auth + Firestore + Vercel. This table shows what the frontend team must follow, in simple words.
# | Governance topic (from brief) | What frontend must do | Status | Simple note
1 | Login / Authentication (JWT) | User signs in on the login page. Every API call sends the Firebase token. Do not store password in localStorage. | Done | Firebase Auth login. Token refresh is automatic. SSO/SAML not in frontend yet.
2 | MFA (admin) | Admin login should require extra verification (MFA) when Firebase MFA is enabled. | Open | Brief says MFA is required for admin. Not turned on yet.
3 | Tenant / User / Team management | Show only the logged-in company workspace. Admin console only for platform admin. Do not let UI hide = security. | Done | RoleRoute: admin → /admin, customer → /dashboard. Suspended account is blocked.
4 | Data security / isolation (RLS) | Frontend must request only own org data. Never list all customers from a customer login. Isolation must also be in Firestore rules. | Done | Rules: customer reads own org only. Admin can list all. Must deploy rules to go live.
5 | Ownership check (no ID guess) | Do not trust a URL or org id from the user. Server / Firestore rules decide if they own it. | Done | Create account only via Cloud Function. No client-side user create.
6 | Secrets never in frontend or git | No API secret keys in React code. VITE_ Firebase keys are public by design. Real secrets stay in Vercel / Functions. | Done | .gitignore covers all .env files. .env.example has empty values.
7 | HTTPS everywhere | App must run on https in production. No http links for login or APIs. | Done | Vercel HTTPS + HSTS header.
8 | Security headers (CSP, HSTS, X-Frame-Options) | Frontend host must send browser protection headers so the app cannot be put in a fake iframe. | Done | Added in vercel.json. Needs Vercel redeploy.
9 | Input validation / XSS | Validate forms on screen (email, password length). Do not render untrusted HTML. Use React text, not innerHTML. | Partial | Login + create-account forms validated. Password min 12. Keep avoiding innerHTML.
10 | Session management | Logout must clear session. Remember-me uses local storage; otherwise session only. Token expires and refreshes. | Partial | Firebase token ~1 hour + refresh. Forced remote logout (revoke) not built yet.
11 | Audit logging | Frontend should not be the source of truth. Sensitive actions (create account, suspend) should be logged on server. | Open | No audit screen / event write yet. Do not log passwords in console.
12 | Logging hygiene / no PII in logs | Do not console.log passwords, tokens, or full customer PII. | Partial | Create-account errors are generic. Review leftover console.error in admin pages.
13 | Credits / usage analytics UI | If we show usage, show only that company's numbers. No cross-company charts for customers. | Open | Admin sees org.totalCalls. Full credits ledger is not a frontend feature yet.
14 | Rate limiting | Frontend cannot fully enforce this. Still: disable double-submit on login/create buttons. | Open | Buttons have loading state. IP rate limit is backend / App Check.
15 | Dependency / supply-chain (frontend) | Keep npm packages updated. Do not add unknown UI libraries without review. | Open | Run npm audit. Add Dependabot later.
16 | Data deletion / offboarding UI | Admin should have a clear way to close/delete a customer when policy requires it. | Open | Suspend exists. Full delete + data wipe UI not built.
Frontend summary for manager
Done on frontend | Login, role routing, tenant isolation (with rules), server-only account create, secrets out of git, HTTPS headers, stronger password, no mock data in prod build.
Partial | Form validation / XSS hygiene, session logout, avoid PII in logs.
Open (frontend + console) | Admin MFA, audit log UI/events, usage ledger, App Check / rate limit, npm audit process, delete-customer UI.
Deploy still needed | Firestore rules + Cloud Functions + Vercel redeploy + VITE_USE_MOCK=false. Until deploy, isolation is in code but not live.
Colour: Green = Done ¦ Amber = Partial ¦ Red = Open