## Frontend Security Table
Voicera Frontend — Security & Compliance Table
Based on HL-SEC-DEVBRIEF-2026-001 ¦ Frontend only ¦ 13 Aug 2026 ¦ Confidential — Internal
Brief stack is Clerk / Supabase / FastAPI / Azure. Voicera frontend uses React + Firebase Auth + Firestore + Vercel. This table shows what the frontend team must follow, in simple words.
# | Governance topic (from brief) | What frontend must do | Status | Simple note
1 | Login / Authentication (JWT) | User signs in on the login page. Every API call sends the Firebase token. Do not store password in localStorage. | Done | Firebase Auth login. Token refresh is automatic. SSO/SAML not in frontend yet.
2 | MFA (admin) | Admin login should require extra verification (MFA) when Firebase MFA is enabled. | Done | TOTP enroll on Admin → Security. Login asks for authenticator code when MFA is on. Enable Identity Platform MFA in Firebase Console.
3 | Tenant / User / Team management | Show only the logged-in company workspace. Admin console only for platform admin. Do not let UI hide = security. | Done | RoleRoute: admin → /admin, customer → /dashboard. Suspended account is blocked.
4 | Data security / isolation (RLS) | Frontend must request only own org data. Never list all customers from a customer login. Isolation must also be in Firestore rules. | Done | Rules: customer reads own org only. Admin can list all. Must deploy rules to go live.
5 | Ownership check (no ID guess) | Do not trust a URL or org id from the user. Server / Firestore rules decide if they own it. | Done | Create account only via Cloud Function. No client-side user create.
6 | Secrets never in frontend or git | No API secret keys in React code. VITE_ Firebase keys are public by design. Real secrets stay in Vercel / Functions. | Done | .gitignore covers all .env files. .env.example has empty values.
7 | HTTPS everywhere | App must run on https in production. No http links for login or APIs. | Done | Vercel HTTPS + HSTS header.
8 | Security headers (CSP, HSTS, X-Frame-Options) | Frontend host must send browser protection headers so the app cannot be put in a fake iframe. | Done | Added in vercel.json. Needs Vercel redeploy.
9 | Input validation / XSS | Validate forms on screen (email, password length). Do not render untrusted HTML. Use React text, not innerHTML. | Done | Email + password policy on login/create. Names sanitised. React text only (no innerHTML).
10 | Session management | Logout must clear session. Remember-me uses local storage; otherwise session only. Token expires and refreshes. | Done | Logout clears storage + revokes refresh tokens. Security page can sign out other devices.
11 | Audit logging | Frontend should not be the source of truth. Sensitive actions (create account, suspend) should be logged on server. | Done | Cloud Function stamps audit_events. Admin Security page lists last 50. Client cannot write the collection.
12 | Logging hygiene / no PII in logs | Do not console.log passwords, tokens, or full customer PII. | Done | safeLog redacts emails/secrets. Admin pages use it instead of raw console.error.
13 | Credits / usage analytics UI | If we show usage, show only that company's numbers. No cross-company charts for customers. | Done | Customer Usage & credits page shows own org calls vs plan limit only.
14 | Rate limiting | Frontend cannot fully enforce this. Still: disable double-submit on login/create buttons. | Done | Client throttle on login / MFA / reset / create-account. Loading disables double-submit. IP limit remains backend.
15 | Dependency / supply-chain (frontend) | Keep npm packages updated. Do not add unknown UI libraries without review. | Done | Dependabot weekly for root + functions. Review PRs before merge.
16 | Data deletion / offboarding UI | Admin should have a clear way to close/delete a customer when policy requires it. | Done | Admin drawer: Offboard / delete account. Cloud Function deletes Auth user + org + audit.
Frontend summary for manager
Done on frontend | Login + MFA step, role routing, tenant isolation, server-only account create/update/offboard, audit log UI, usage (own org), validation, safe logs, session revoke, Dependabot, HTTPS headers.
Partial | None remaining on the frontend table. App Check / IP rate limit still sit on Firebase / backend.
Open (ops / console) | Enable Identity Platform TOTP MFA in Firebase Console. Deploy rules + functions + Vercel.
Deploy still needed | Firestore rules + Cloud Functions + Vercel redeploy + VITE_USE_MOCK=false. Until deploy, isolation is in code but not live.
Colour: Green = Done ¦ Amber = Partial ¦ Red = Open