## Security Status
Voicera — Production Security Status
Simple status for manager review ¦ 13 Aug 2026 ¦ Confidential — Internal
In one line: core security (who can see whose data) is now in the code. It still needs to be deployed, then MFA and audit log can follow.
# | Security topic | Status | What this means (plain English) | What to do next
1 | Login / who is the user | Done | Users sign in with Firebase. After login they get a token. Admin goes to Admin Console, customer goes to their dashboard. | Keep using Firebase login. Turn on MFA for admin accounts later.
2 | One customer cannot see another customer's data | Done | Each company (tenant) can only read their own record. Only Platform Admin can see the full customer list or change accounts. | Deploy Firestore rules to production so this is live.
3 | Who can create a new customer account | Done | Only Platform Admin, and only through the server (Cloud Function). The browser can no longer create users by itself. | Deploy Cloud Functions to production.
4 | Passwords & secrets not stored in GitHub | Done | Env files and Firebase key files are ignored by git. Example env file has empty placeholders only. | Confirm Vercel has real keys in dashboard env, not in the repo.
5 | Website security headers (HTTPS, clickjacking, etc.) | Done | Vercel now sends extra browser protections (HSTS, CSP, no iframe embed). | Redeploy the frontend on Vercel.
6 | Mock / dummy data in production | Done | Production build will not show fake demo data even if someone forgets the env flag. | Set VITE_USE_MOCK=false in Vercel environment.
7 | Strong password for new customers | Done | New account password must be at least 12 characters (UI + server). | No extra action after deploy.
8 | Admin extra login (MFA) | Open | Brief asks that admin/owner must use MFA. This is not turned on yet in Firebase. | Enable MFA for platform admin emails in Firebase Console.
9 | Audit log (who did what, when) | Open | Enterprise customers always ask for this. Voicera does not store an activity log yet. | Plan a simple audit table: user, action, time, company.
10 | Rate limit / bot protection | Open | Brief asks to limit how many requests one IP can make. Not added yet. | Turn on Firebase App Check (and WAF later).
11 | Backup & incident plan | Open | No written backup/restore or incident response document for Voicera yet. | Write a 1-page backup + incident note for the team.
Quick summary
Done now (in code) | Login, tenant isolation, admin-only account create, secrets out of git, security headers, no mock in prod, stronger password.
Must deploy this week | 1) Firestore rules 2) Cloud Functions 3) Vercel frontend 4) VITE_USE_MOCK=false
Do next (after deploy) | Admin MFA, App Check, audit log, backup/incident note.
Production ready? | Not yet. Ready after the deploy steps above. Then we can say “production hardening started / core isolation live.”
Colour key: Green = Done ¦ Amber = In progress ¦ Red = Open / not started

## Next actions
Next actions (checklist)
Update Status using the dropdown. This is the only follow-up sheet.
When | Action | Who | Status
This week | Deploy Firestore rules to production | DevOps / Eng | Not Started
This week | Deploy Cloud Functions to production | DevOps / Eng | Not Started
This week | Redeploy frontend on Vercel | DevOps / Eng | Not Started
This week | Set VITE_USE_MOCK=false on Vercel | DevOps | Not Started
This week | Set platform_admin role on admin users | Eng | Not Started
Next sprint | Turn on MFA for admin accounts | Eng + IT | Not Started
Next sprint | Turn on Firebase App Check | Eng | Not Started
Later | Add audit log (who did what) | Eng | Not Started
Later | Write backup + incident 1-pager | Eng + Manager | Not Started